ENGAGEMENT DOCUMENT · BLA 2026 COMPLIANCE SPRINT Sprint Work Order Bangladesh Labour (Amendment) Act 2026 — Factory Compliance Documentation Sprint Reference VNT-SWO-001; Issue Date [Insert Date]; Valid Until [30 days from issue]; Status AWAITING ACCEPTANCE.

| PREPARED FOR Factory / Company Name: _________________________________ Contact Person / MD Name: _________________________________ Factory Address: _________________________________ Primary Buyer(s): _________________________________ Approx. Worker Headcount: _________________________________ |  | PREPARED BY VANTAGE Compliance Documentation & Advisory Operated by Keystone Consultancy Munim Founder & CEO 📱 +8801941646278 ✉ munimhasibul10@gmail.com 🌐 govantage.vercel.app |
| --- | --- | --- |

Engagement Overview

VANTAGE will conduct a focused compliance documentation sprint to assess, organise, and remedy all outstanding obligations of the Client under the Bangladesh Labour (Amendment) Act 2026. The Sprint is a fixed-scope, fixed-fee engagement completed within 5–7 working days of commencement. Every deliverable is handed over in both physical and digital form, permanently organised in a Google Drive folder accessible to the Client.

| ⏱ Duration 5–7 Working Days from advance payment receipt |  | 📍 Location On-site at Factory + Digital delivery via Google Drive |  | 📋 MSA Required Yes — Prior to Commencement Keystone Consultancy standard MSA |
| --- | --- | --- | --- | --- |

Select Your Sprint Tier

| TIER 1 Basic Sprint 35,000 BDT ✓ BLA 2026 Gap Analysis Report ✓ Employee Handbook Insert (Bangla) ✓ Digital Evidence Package SELECT THIS TIER ☐ Client Initials: ______ |  | ★ RECOMMENDED TIER 2 Standard Sprint 55,000 BDT ✓ All Basic Sprint deliverables ✓ Anti-Blacklisting Compliance File ✓ Supervisor Training (2 hrs) ✓ Buyer Notification Letter ✓ Full Digital Evidence Package MOST POPULAR ☐ Client Initials: ______ |  | TIER 3 Premium Sprint 75,000 BDT ✓ All Standard Sprint deliverables ✓ 3-Month Follow-Up Support ✓ Pre-Audit WhatsApp Hotline ✓ Second Gap Scan at Month 3 ✓ Priority Subscription offer SELECT THIS TIER ☐ Client Initials: ______ |
| --- | --- | --- | --- | --- |

What You Receive — Standard Sprint (Tier 2)

The Standard Sprint (Tier 2) is the recommended engagement for most factories. All 6 deliverables below are included. Each item is provided in physical copy and as a permanently accessible digital file.

| 01 | BLA 2026 Gap Analysis Report Red / Yellow / Green findings table mapping current factory practices against BLA 2026 requirements. Buyer-ready format, English + Bangla sections. |
| --- | --- |

| 02 | Anti-Blacklisting Compliance File Full review of all HR records and any existing personnel databases. Written recommendation to destroy, retain, or reclassify each document. Legal advisory note included. |
| --- | --- |

| 03 | Updated Employee Handbook Insert 4-page insert covering new maternity leave (120 days), festival leave (13 days), anti-blacklisting policy, and provident fund obligations. Simple Bangla — worker-readable. |
| --- | --- |

| 04 | Supervisor Training Session 2-hour on-site training delivered by Vantage. Attendance sheet, participant photos, and training record provided as audit evidence. Covers all BLA 2026 obligations relevant to supervisors. |
| --- | --- |

| 05 | Buyer Notification Letter Professional letter on Keystone Consultancy letterhead addressed to the factory's primary buyer confirming completion of BLA 2026 compliance documentation review. |
| --- | --- |

| 06 | Digital Evidence Package (Permanent) All five deliverables above compiled into a single organised Google Drive folder shared with the factory permanently. Accessible at any time, including during an actual audit. |
| --- | --- |

What We Need From You

| Documents to Provide - Current employee handbook or HR policy file - Last 6 months' payroll or wage ledger - Existing personnel database or termination records - Current maternity / leave policy (if documented) - List of supervisors for training session - Primary buyer name and contact | Access Required - Factory access for 1 site visit (half-day) - Meeting with HR Manager or Compliance Officer - Access to training room / meeting area for supervisor training - WhatsApp contact for real-time document requests |
| --- | --- |

Investment & Payment Schedule

SELECTED TIER Standard Sprint (Tier 2) 6 Deliverables · 5–7 Working Days; TOTAL ENGAGEMENT FEE BDT 55,000 Compare: 1 failed audit = BDT 15–50 lakh lost.

| TIMING | MILESTONE | AMOUNT | NOTE |
| --- | --- | --- | --- |
| Day 0 | Advance Payment — before commencement of any work | BDT 27,500 | 50% |
| Day 5–7 | Final Delivery of all 6 Deliverables | BDT 27,500 | 50% |
| TOTAL | Full Sprint Engagement — Standard Tier | BDT 55,000 | Fixed |

Payment accepted via: Bank Transfer (Keystone Consultancy account — details on invoice)  |  bKash Merchant  |  Nagad Business

Key Terms

| Non-Refundable Advance The 50% advance payment is non-refundable once work commences. Role Limitation Vantage provides documentation preparation and advisory support only. We do not conduct official compliance audits, issue certifications, or guarantee audit outcomes. | Client Cooperation Delayed document submission or denied factory access will extend the delivery timeline. Vantage is not liable for delays caused by Client. Governing Law & Liability This Work Order is governed by the laws of Bangladesh and is subject to the MSA signed separately. Total liability capped at fees paid in the three months prior to any claim. |
| --- | --- |

Acceptance

By signing below, the Client confirms they have read and understood this Work Order and the Master Services Agreement, authorise the commencement of the Sprint upon advance payment, and accept the payment obligations stated herein.

সই করার মাধ্যমে ক্লায়েন্ট নিশ্চিত করছেন যে তিনি এই ওয়ার্ক অর্ডার পড়েছেন, বুঝেছেন এবং সব শর্তে সম্মত হয়েছেন।

| CLIENT Signature: ________________________________ Printed Name: ________________________________ Title / Designation: ________________________________ Date: ________________________________ Company Stamp: ________________________________ [Factory Name] |  | SERVICE PROVIDER Signature: ________________________________ Printed Name: Munim Title: Founder & CEO Date: ________________________________ Company Stamp: ________________________________ Keystone Consultancy (operating as VANTAGE) |
| --- | --- | --- |

Document Ref: VNT-SWO-001  ·  Version 1.0  ·  Governed by Bangladesh Law  ·  VANTAGE / Keystone Consultancy